## Milestones
Milestones tracker
As of | 2026-10-16T00:00:00.000Z | Fictional PMO training data. No real Synechron project information.
Milestone ID | Project | Milestone | Owner | Due Date | Completed Date | Status | Progress | Reported RAG | Last Update | Comments | Dependency
M01 | Atlas Onboarding | Requirements sign-off | Asha Rao | 2026-10-12T00:00:00.000Z | 2026-10-12T00:00:00.000Z | Completed | 100% | Green | 2026-10-12T00:00:00.000Z | Signed off by business lead | None
M02 | Atlas Onboarding | API integration | Rohan Mehta | 2026-10-15T00:00:00.000Z |  | Blocked | 65% | Red | 2026-10-16T00:00:00.000Z | Sandbox access still pending | Vendor sandbox access
M03 | Atlas Onboarding | Integration testing | Neha Shah | 2026-10-21T00:00:00.000Z |  | Not Started | 0% | Amber | 2026-10-16T00:00:00.000Z | Depends on M02 | M02
M04 | Atlas Onboarding | Release readiness | Asha Rao | 2026-10-23T00:00:00.000Z |  | Not Started | 0% | Amber | 2026-10-16T00:00:00.000Z | Readiness review scheduled | M03
M05 | Beacon Reporting | Data mapping | Kavya Iyer | 2026-10-09T00:00:00.000Z | 2026-10-09T00:00:00.000Z | Completed | 100% | Green | 2026-10-09T00:00:00.000Z | Mapping accepted | None
M06 | Beacon Reporting | Data validation | Arjun Sen | 2026-10-14T00:00:00.000Z |  | In Progress | 80% | Amber | 2026-10-15T00:00:00.000Z | Two source mappings unresolved | Business clarification
M07 | Beacon Reporting | UAT sign-off | Kavya Iyer | 2026-10-22T00:00:00.000Z |  | Not Started | 0% | Amber | 2026-10-16T00:00:00.000Z | Testers nominated | M06
M08 | Beacon Reporting | Support handover | Vikram Das | 2026-10-26T00:00:00.000Z |  | Not Started | 0% | Green | 2026-10-09T00:00:00.000Z | Draft runbook pending | M07
M09 | Cedar Migration | Environment readiness | Farah Khan | 2026-10-13T00:00:00.000Z | 2026-10-13T00:00:00.000Z | Completed | 100% | Green | 2026-10-13T00:00:00.000Z | Environment checks complete | None
M10 | Cedar Migration | Security review | Dev Patel | 2026-10-16T00:00:00.000Z |  | In Progress | 90% | Amber | 2026-10-16T00:00:00.000Z | One review finding open | Security reviewer
M11 | Cedar Migration | Migration rehearsal | Farah Khan | 2026-10-20T00:00:00.000Z |  | Not Started | 0% | Amber | 2026-10-16T00:00:00.000Z | Depends on security clearance | M10
M12 | Cedar Migration | Operations handover |  | 2026-10-23T00:00:00.000Z |  | Not Started | 0% | Green | 2026-10-08T00:00:00.000Z | Owner assignment required | M11

## Actions
Actions tracker
As of | 2026-10-16T00:00:00.000Z | Fictional PMO training data. No real Synechron project information.
Action ID | Project | Action | Owner | Due Date | Status | Priority | Milestone ID | Comments
A01 | Atlas Onboarding | Obtain sandbox access | Rohan Mehta | 2026-10-14T00:00:00.000Z | Open | High | M02 | Vendor has not confirmed access
A02 | Atlas Onboarding | Confirm test slot | Neha Shah | 2026-10-19T00:00:00.000Z | Open | Medium | M03 | Awaiting API completion
A03 | Beacon Reporting | Resolve source mappings | Arjun Sen | 2026-10-15T00:00:00.000Z | In Progress | High | M06 | Two mappings require business input
A04 | Beacon Reporting | Nominate UAT testers | Kavya Iyer | 2026-10-16T00:00:00.000Z | Completed | Medium | M07 | Testers confirmed on 16 October
A05 | Cedar Migration | Close security finding | Dev Patel | 2026-10-16T00:00:00.000Z | In Progress | High | M10 | Evidence sent to security reviewer
A06 | Cedar Migration | Assign handover owner |  | 2026-10-19T00:00:00.000Z | Open | High | M12 | Sponsor must assign owner
A07 | Beacon Reporting | Draft support runbook | Vikram Das |  | Open | Medium | M08 | Due date not agreed
A08 | Atlas Onboarding | Archive sign-off | Asha Rao | 2026-10-13T00:00:00.000Z | Completed | Low | M01 | Evidence archived

## RAID
RAID tracker
As of | 2026-10-16T00:00:00.000Z | Fictional PMO training data. No real Synechron project information.
RAID ID | Project | Type | Description | Impact | Owner | Status | Review Date | Response | Milestone ID
R01 | Atlas Onboarding | Issue | Sandbox access unavailable | High | Rohan Mehta | Open | 2026-10-19T00:00:00.000Z | Escalate access request to vendor lead | M02
R02 | Beacon Reporting | Risk | UAT may slip if mappings remain open | Medium | Kavya Iyer | Open | 2026-10-20T00:00:00.000Z | Confirm mappings before UAT | M07
R03 | Cedar Migration | Dependency | Security clearance required for rehearsal | High | Dev Patel | Open | 2026-10-16T00:00:00.000Z | Obtain reviewer decision | M11
R04 | Beacon Reporting | Assumption | Business testers available on 22 October | Medium | Kavya Iyer | Open | 2026-10-19T00:00:00.000Z | Confirm availability with business lead | M07
R05 | Cedar Migration | Issue | Environment setup delay | Low | Farah Khan | Closed | 2026-10-13T00:00:00.000Z | Environment completed on 13 October | M09