## Resource Allocation
Employee Name | Role | Project Name | Week Start Date | Allocation % | Billable (Y/N)
Aditi Rao | Business Analyst | Loan Origination Revamp | 2026-08-25 | 60 | Y
Aditi Rao | Business Analyst | Loan Origination Revamp | 2026-09-01 | 65 | Y
Aditi Rao | Business Analyst | Loan Origination Revamp | 2026-09-08 | 70 | Y
Aditi Rao | Business Analyst | Loan Origination Revamp | 2026-09-15 | 75 | Y
Aditi Rao | Business Analyst | Collections Dashboard | 2026-08-25 | 30 | Y
Aditi Rao | Business Analyst | Collections Dashboard | 2026-09-01 | 30 | Y
Aditi Rao | Business Analyst | Collections Dashboard | 2026-09-08 | 30 | Y
Aditi Rao | Business Analyst | Collections Dashboard | 2026-09-15 | 30 | Y
Rohan Mehta | PMO Analyst | Loan Origination Revamp | 2026-08-25 | 30 | Y
Rohan Mehta | PMO Analyst | Loan Origination Revamp | 2026-09-01 | 30 | Y
Rohan Mehta | PMO Analyst | Loan Origination Revamp | 2026-09-08 | 30 | Y
Rohan Mehta | PMO Analyst | Loan Origination Revamp | 2026-09-15 | 30 | Y
Rohan Mehta | PMO Analyst | Vendor Onboarding Portal | 2026-08-25 | 30 | Y
Rohan Mehta | PMO Analyst | Vendor Onboarding Portal | 2026-09-01 | 35 | Y
Rohan Mehta | PMO Analyst | Vendor Onboarding Portal | 2026-09-08 | 40 | Y
Rohan Mehta | PMO Analyst | Vendor Onboarding Portal | 2026-09-15 | 45 | Y
Rohan Mehta | PMO Analyst | Compliance Reporting Upgrade | 2026-08-25 | 20 | N
Rohan Mehta | PMO Analyst | Compliance Reporting Upgrade | 2026-09-01 | 20 | N
Rohan Mehta | PMO Analyst | Compliance Reporting Upgrade | 2026-09-08 | 20 | N
Rohan Mehta | PMO Analyst | Compliance Reporting Upgrade | 2026-09-15 | 20 | N
Sneha Kulkarni | Project Coordinator | Vendor Onboarding Portal | 2026-08-25 | 50 | Y
Sneha Kulkarni | Project Coordinator | Vendor Onboarding Portal | 2026-09-01 | 55 | Y
Sneha Kulkarni | Project Coordinator | Vendor Onboarding Portal | 2026-09-08 | 60 | Y
Sneha Kulkarni | Project Coordinator | Vendor Onboarding Portal | 2026-09-15 | 65 | Y
Sneha Kulkarni | Project Coordinator | Compliance Reporting Upgrade | 2026-08-25 | 20 | N
Sneha Kulkarni | Project Coordinator | Compliance Reporting Upgrade | 2026-09-01 | 20 | N
Sneha Kulkarni | Project Coordinator | Compliance Reporting Upgrade | 2026-09-08 | 20 | N
Sneha Kulkarni | Project Coordinator | Compliance Reporting Upgrade | 2026-09-15 | 20 | N
Karan Bhatia | Senior PM | Collections Dashboard | 2026-08-25 | 70 | Y
Karan Bhatia | Senior PM | Collections Dashboard | 2026-09-01 | 70 | Y
Karan Bhatia | Senior PM | Collections Dashboard | 2026-09-08 | 70 | Y
Karan Bhatia | Senior PM | Collections Dashboard | 2026-09-15 | 70 | Y
Karan Bhatia | Senior PM | Digital KYC Enhancement | 2026-08-25 | 20 | Y
Karan Bhatia | Senior PM | Digital KYC Enhancement | 2026-09-01 | 25 | Y
Karan Bhatia | Senior PM | Digital KYC Enhancement | 2026-09-08 | 30 | Y
Karan Bhatia | Senior PM | Digital KYC Enhancement | 2026-09-15 | 35 | Y
Priya Nair | PMO Lead | Loan Origination Revamp | 2026-08-25 | 20 | Y
Priya Nair | PMO Lead | Loan Origination Revamp | 2026-09-01 | 20 | Y
Priya Nair | PMO Lead | Loan Origination Revamp | 2026-09-08 | 20 | Y
Priya Nair | PMO Lead | Loan Origination Revamp | 2026-09-15 | 20 | Y
Priya Nair | PMO Lead | Vendor Onboarding Portal | 2026-08-25 | 20 | Y
Priya Nair | PMO Lead | Vendor Onboarding Portal | 2026-09-01 | 20 | Y
Priya Nair | PMO Lead | Vendor Onboarding Portal | 2026-09-08 | 20 | Y
Priya Nair | PMO Lead | Vendor Onboarding Portal | 2026-09-15 | 20 | Y
Priya Nair | PMO Lead | Compliance Reporting Upgrade | 2026-08-25 | 20 | N
Priya Nair | PMO Lead | Compliance Reporting Upgrade | 2026-09-01 | 20 | N
Priya Nair | PMO Lead | Compliance Reporting Upgrade | 2026-09-08 | 20 | N
Priya Nair | PMO Lead | Compliance Reporting Upgrade | 2026-09-15 | 20 | N
Priya Nair | PMO Lead | Branch Analytics Rollout | 2026-08-25 | 10 | Y
Priya Nair | PMO Lead | Branch Analytics Rollout | 2026-09-01 | 10 | Y
Priya Nair | PMO Lead | Branch Analytics Rollout | 2026-09-08 | 10 | Y
Priya Nair | PMO Lead | Branch Analytics Rollout | 2026-09-15 | 10 | Y
Amit Deshmukh | Business Analyst | Compliance Reporting Upgrade | 2026-08-25 | 60 | N
Amit Deshmukh | Business Analyst | Compliance Reporting Upgrade | 2026-09-01 | 55 | N
Amit Deshmukh | Business Analyst | Compliance Reporting Upgrade | 2026-09-08 | 50 | N
Amit Deshmukh | Business Analyst | Compliance Reporting Upgrade | 2026-09-15 | 45 | N
Amit Deshmukh | Business Analyst | Loan Origination Revamp | 2026-08-25 | 30 | Y
Amit Deshmukh | Business Analyst | Loan Origination Revamp | 2026-09-01 | 30 | Y
Amit Deshmukh | Business Analyst | Loan Origination Revamp | 2026-09-08 | 30 | Y
Amit Deshmukh | Business Analyst | Loan Origination Revamp | 2026-09-15 | 30 | Y
Farida Sheikh | Project Coordinator | Employee Self-Service Portal | 2026-08-25 | 70 | Y
Farida Sheikh | Project Coordinator | Employee Self-Service Portal | 2026-09-01 | 70 | Y
Farida Sheikh | Project Coordinator | Employee Self-Service Portal | 2026-09-08 | 70 | Y
Farida Sheikh | Project Coordinator | Employee Self-Service Portal | 2026-09-15 | 70 | Y
Farida Sheikh | Project Coordinator | Vendor Onboarding Portal | 2026-08-25 | 20 | Y
Farida Sheikh | Project Coordinator | Vendor Onboarding Portal | 2026-09-01 | 25 | Y
Farida Sheikh | Project Coordinator | Vendor Onboarding Portal | 2026-09-08 | 30 | Y
Farida Sheikh | Project Coordinator | Vendor Onboarding Portal | 2026-09-15 | 35 | Y
Vikram Joshi | Senior PM | Employee Self-Service Portal | 2026-08-25 | 50 | Y
Vikram Joshi | Senior PM | Employee Self-Service Portal | 2026-09-01 | 45 | Y
Vikram Joshi | Senior PM | Employee Self-Service Portal | 2026-09-08 | 40 | Y
Vikram Joshi | Senior PM | Employee Self-Service Portal | 2026-09-15 | 35 | Y
Vikram Joshi | Senior PM | Collections Dashboard | 2026-08-25 | 20 | Y
Vikram Joshi | Senior PM | Collections Dashboard | 2026-09-01 | 20 | Y
Vikram Joshi | Senior PM | Collections Dashboard | 2026-09-08 | 20 | Y
Vikram Joshi | Senior PM | Collections Dashboard | 2026-09-15 | 20 | Y
Neha Kapoor | Senior PM | Digital KYC Enhancement | 2026-08-25 | 60 | Y
Neha Kapoor | Senior PM | Digital KYC Enhancement | 2026-09-01 | 65 | Y
Neha Kapoor | Senior PM | Digital KYC Enhancement | 2026-09-08 | 70 | Y
Neha Kapoor | Senior PM | Digital KYC Enhancement | 2026-09-15 | 75 | Y
Neha Kapoor | Senior PM | Loan Origination Revamp | 2026-08-25 | 20 | Y
Neha Kapoor | Senior PM | Loan Origination Revamp | 2026-09-01 | 20 | Y
Neha Kapoor | Senior PM | Loan Origination Revamp | 2026-09-08 | 20 | Y
Neha Kapoor | Senior PM | Loan Origination Revamp | 2026-09-15 | 20 | Y
Suresh Iyer | Senior PM | Branch Analytics Rollout | 2026-08-25 | 70 | Y
Suresh Iyer | Senior PM | Branch Analytics Rollout | 2026-09-01 | 70 | Y
Suresh Iyer | Senior PM | Branch Analytics Rollout | 2026-09-08 | 70 | Y
Suresh Iyer | Senior PM | Branch Analytics Rollout | 2026-09-15 | 85 | Y
Suresh Iyer | Senior PM | Digital KYC Enhancement | 2026-08-25 | 10 | Y
Suresh Iyer | Senior PM | Digital KYC Enhancement | 2026-09-01 | 10 | Y
Suresh Iyer | Senior PM | Digital KYC Enhancement | 2026-09-08 | 10 | Y
Suresh Iyer | Senior PM | Digital KYC Enhancement | 2026-09-15 | 10 | Y
Ritu Malhotra | Business Analyst | Digital KYC Enhancement | 2026-08-25 | 40 | Y
Ritu Malhotra | Business Analyst | Digital KYC Enhancement | 2026-09-01 | 45 | Y
Ritu Malhotra | Business Analyst | Digital KYC Enhancement | 2026-09-08 | 50 | Y
Ritu Malhotra | Business Analyst | Digital KYC Enhancement | 2026-09-15 | 55 | Y
Ritu Malhotra | Business Analyst | Branch Analytics Rollout | 2026-08-25 | 30 | Y
Ritu Malhotra | Business Analyst | Branch Analytics Rollout | 2026-09-01 | 30 | Y
Ritu Malhotra | Business Analyst | Branch Analytics Rollout | 2026-09-08 | 30 | Y
Ritu Malhotra | Business Analyst | Branch Analytics Rollout | 2026-09-15 | 30 | Y
Arjun Menon | PMO Analyst | Branch Analytics Rollout | 2026-08-25 | 40 | Y
Arjun Menon | PMO Analyst | Branch Analytics Rollout | 2026-09-01 | 40 | Y
Arjun Menon | PMO Analyst | Branch Analytics Rollout | 2026-09-08 | 40 | Y
Arjun Menon | PMO Analyst | Branch Analytics Rollout | 2026-09-15 | 40 | Y
Arjun Menon | PMO Analyst | Compliance Reporting Upgrade | 2026-08-25 | 20 | N
Arjun Menon | PMO Analyst | Compliance Reporting Upgrade | 2026-09-01 | 25 | N
Arjun Menon | PMO Analyst | Compliance Reporting Upgrade | 2026-09-08 | 30 | N
Arjun Menon | PMO Analyst | Compliance Reporting Upgrade | 2026-09-15 | 35 | N

## Allocation Trend Summary
Employee Name | Wk1 Total % (25-Aug) | Wk2 Total % (01-Sep) | Wk3 Total % (08-Sep) | Wk4 Total % (15-Sep) | Trend (Wk4 - Wk1) | Status (Wk4)
Aditi Rao | 90 | 95 | 100 | 105 | 15 | Overallocated
Rohan Mehta | 80 | 85 | 90 | 95 | 15 | Optimal
Sneha Kulkarni | 70 | 75 | 80 | 85 | 15 | Optimal
Karan Bhatia | 90 | 95 | 100 | 105 | 15 | Overallocated
Priya Nair | 70 | 70 | 70 | 70 | 0 | Optimal
Amit Deshmukh | 90 | 85 | 80 | 75 | -15 | Optimal
Farida Sheikh | 90 | 95 | 100 | 105 | 15 | Overallocated
Vikram Joshi | 70 | 65 | 60 | 55 | -15 | Underutilized
Neha Kapoor | 80 | 85 | 90 | 95 | 15 | Optimal
Suresh Iyer | 80 | 80 | 80 | 95 | 15 | Optimal
Ritu Malhotra | 70 | 75 | 80 | 85 | 15 | Optimal
Arjun Menon | 60 | 65 | 70 | 75 | 15 | Optimal
Trend column shows the change in total allocation from Week 1 to Week 4. A large positive number flags someone heading toward overallocation before it becomes a problem.

## Project Status
Project Name | Project Manager | Sponsor | Week Start Date | % Complete | RAG Status | Planned Budget (INR) | Actual Spend to Date (INR) | Planned Spend to Date (INR) | Budget Variance % | Open High-Impact Risks | Risk Cost Exposure (INR) | Key Risk / Issue | Next Milestone | Milestone Date
Loan Origination Revamp | Karan Bhatia | Head - Retail Lending | 2026-08-25 | 40 | Amber | 8500000 | 3000000 | 3400000 | -11.76% | 1 | 450000 | Vendor API delivery slipped by 2 weeks | UAT sign-off | 2026-10-05
Loan Origination Revamp | Karan Bhatia | Head - Retail Lending | 2026-09-01 | 45 | Amber | 8500000 | 3600000 | 3825000 | -5.882% | 1 | 450000 | Vendor API delivery slipped by 2 weeks | UAT sign-off | 2026-10-05
Loan Origination Revamp | Karan Bhatia | Head - Retail Lending | 2026-09-08 | 50 | Amber | 8500000 | 4300000 | 4250000 | 1.176% | 1 | 450000 | Vendor API delivery slipped by 2 weeks | UAT sign-off | 2026-10-05
Loan Origination Revamp | Karan Bhatia | Head - Retail Lending | 2026-09-15 | 55 | Amber | 8500000 | 5100000 | 4675000 | 9.091% | 1 | 450000 | Vendor API delivery slipped by 2 weeks | UAT sign-off | 2026-10-05
Collections Dashboard | Karan Bhatia | Head - Collections | 2026-08-25 | 65 | Green | 3200000 | 1800000 | 2080000 | -13.46% | 0 | 0 | None flagged | Go-live | 2026-09-25
Collections Dashboard | Karan Bhatia | Head - Collections | 2026-09-01 | 70 | Green | 3200000 | 2100000 | 2240000 | -6.25% | 0 | 0 | None flagged | Go-live | 2026-09-25
Collections Dashboard | Karan Bhatia | Head - Collections | 2026-09-08 | 75 | Green | 3200000 | 2450000 | 2400000 | 2.083% | 0 | 0 | None flagged | Go-live | 2026-09-25
Collections Dashboard | Karan Bhatia | Head - Collections | 2026-09-15 | 80 | Green | 3200000 | 2700000 | 2560000 | 5.469% | 0 | 0 | None flagged | Go-live | 2026-09-25
Vendor Onboarding Portal | Priya Nair | Head - Procurement | 2026-08-25 | 15 | Amber | 5000000 | 1200000 | 750000 | 60% | 2 | 1300000 | Spend outpacing progress; migration approach unresolved | Migration plan sign-off | 2026-09-22
Vendor Onboarding Portal | Priya Nair | Head - Procurement | 2026-09-01 | 20 | Amber | 5000000 | 1900000 | 1000000 | 90% | 2 | 1300000 | Spend outpacing progress; migration approach unresolved | Migration plan sign-off | 2026-09-22
Vendor Onboarding Portal | Priya Nair | Head - Procurement | 2026-09-08 | 25 | Red | 5000000 | 2800000 | 1250000 | 124% | 2 | 1300000 | Spend outpacing progress; migration approach unresolved | Migration plan sign-off | 2026-09-22
Vendor Onboarding Portal | Priya Nair | Head - Procurement | 2026-09-15 | 30 | Red | 5000000 | 3900000 | 1500000 | 160% | 2 | 1300000 | Spend outpacing progress; migration approach unresolved | Migration plan sign-off | 2026-09-22
Compliance Reporting Upgrade | Priya Nair | Chief Compliance Officer | 2026-08-25 | 50 | Amber | 4000000 | 1600000 | 2000000 | -20% | 1 | 350000 | Regulatory format change expected in Q4 | Regulator preview session | 2026-10-12
Compliance Reporting Upgrade | Priya Nair | Chief Compliance Officer | 2026-09-01 | 55 | Amber | 4000000 | 2000000 | 2200000 | -9.091% | 1 | 350000 | Regulatory format change expected in Q4 | Regulator preview session | 2026-10-12
Compliance Reporting Upgrade | Priya Nair | Chief Compliance Officer | 2026-09-08 | 60 | Amber | 4000000 | 2450000 | 2400000 | 2.083% | 1 | 350000 | Regulatory format change expected in Q4 | Regulator preview session | 2026-10-12
Compliance Reporting Upgrade | Priya Nair | Chief Compliance Officer | 2026-09-15 | 65 | Amber | 4000000 | 2900000 | 2600000 | 11.54% | 1 | 350000 | Regulatory format change expected in Q4 | Regulator preview session | 2026-10-12
Employee Self-Service Portal | Vikram Joshi | Head - HR Operations | 2026-08-25 | 75 | Green | 2800000 | 1900000 | 2100000 | -9.524% | 0 | 0 | None flagged | Production cutover | 2026-09-30
Employee Self-Service Portal | Vikram Joshi | Head - HR Operations | 2026-09-01 | 80 | Green | 2800000 | 2050000 | 2240000 | -8.482% | 0 | 0 | None flagged | Production cutover | 2026-09-30
Employee Self-Service Portal | Vikram Joshi | Head - HR Operations | 2026-09-08 | 85 | Green | 2800000 | 2200000 | 2380000 | -7.563% | 0 | 0 | None flagged | Production cutover | 2026-09-30
Employee Self-Service Portal | Vikram Joshi | Head - HR Operations | 2026-09-15 | 90 | Green | 2800000 | 2350000 | 2520000 | -6.746% | 0 | 0 | None flagged | Production cutover | 2026-09-30
Digital KYC Enhancement | Neha Kapoor | Head - Retail Lending | 2026-08-25 | 20 | Amber | 6000000 | 1500000 | 1200000 | 25% | 1 | 500000 | Third-party ID verification API still in beta | Vendor API certification | 2026-10-01
Digital KYC Enhancement | Neha Kapoor | Head - Retail Lending | 2026-09-01 | 30 | Amber | 6000000 | 2200000 | 1800000 | 22.22% | 1 | 500000 | Third-party ID verification API still in beta | Vendor API certification | 2026-10-01
Digital KYC Enhancement | Neha Kapoor | Head - Retail Lending | 2026-09-08 | 40 | Amber | 6000000 | 3000000 | 2400000 | 25% | 1 | 500000 | Third-party ID verification API still in beta | Vendor API certification | 2026-10-01
Digital KYC Enhancement | Neha Kapoor | Head - Retail Lending | 2026-09-15 | 50 | Green | 6000000 | 3800000 | 3000000 | 26.67% | 1 | 500000 | Third-party ID verification API still in beta | Vendor API certification | 2026-10-01
Branch Analytics Rollout | Suresh Iyer | Head - Network Ops | 2026-08-25 | 10 | Red | 3500000 | 500000 | 350000 | 42.86% | 0 | 0 | Recovering after early adoption issues; Wk4 resourcing surge underway | Regional rollout complete | 2026-10-08
Branch Analytics Rollout | Suresh Iyer | Head - Network Ops | 2026-09-01 | 20 | Amber | 3500000 | 1100000 | 700000 | 57.14% | 0 | 0 | Recovering after early adoption issues; Wk4 resourcing surge underway | Regional rollout complete | 2026-10-08
Branch Analytics Rollout | Suresh Iyer | Head - Network Ops | 2026-09-08 | 30 | Amber | 3500000 | 1700000 | 1050000 | 61.9% | 0 | 0 | Recovering after early adoption issues; Wk4 resourcing surge underway | Regional rollout complete | 2026-10-08
Branch Analytics Rollout | Suresh Iyer | Head - Network Ops | 2026-09-15 | 45 | Amber | 3500000 | 2600000 | 1575000 | 65.08% | 0 | 0 | Recovering after early adoption issues; Wk4 resourcing surge underway | Regional rollout complete | 2026-10-08

## RAID Log
ID | Type | Category | Project Name | Description | Owner | Impact | Estimated Cost Impact (INR) | Status | Date Raised | Target Resolution
RAID-001 | Risk | Vendor/Third-Party | Loan Origination Revamp | Vendor may miss API delivery date again | Rohan Mehta | High | 450000 | Open | 2026-09-01 | 2026-09-20
RAID-002 | Issue | Technical | Loan Origination Revamp | Test environment unavailable for 3 days | Aditi Rao | Medium | 80000 | Mitigated | 2026-08-28 | 2026-09-05
RAID-003 | Risk | Resourcing | Loan Origination Revamp | Business Analyst bandwidth shrinking as allocation rises elsewhere | Priya Nair | Medium | 0 | Open | 2026-09-10 | 2026-09-25
RAID-004 | Assumption | Data | Collections Dashboard | Source data feed remains unchanged through go-live | Vikram Joshi | Low | 0 | Open | 2026-09-02 | 2026-09-25
RAID-005 | Dependency | Technical | Collections Dashboard | Depends on Data Warehouse refresh job completing nightly | Karan Bhatia | Medium | 0 | Open | 2026-09-03 | 2026-09-25
RAID-006 | Issue | Process | Collections Dashboard | Sign-off checklist missing two approver signatures | Karan Bhatia | Low | 0 | Closed | 2026-08-20 | 2026-08-27
RAID-007 | Risk | Process | Vendor Onboarding Portal | Data migration approach not yet approved by Legal | Priya Nair | High | 600000 | Open | 2026-09-04 | 2026-09-22
RAID-008 | Risk | Resourcing | Vendor Onboarding Portal | Key vendor SME on extended leave | Sneha Kulkarni | Medium | 150000 | Open | 2026-09-06 | 2026-09-30
RAID-009 | Issue | Data | Vendor Onboarding Portal | Duplicate vendor records found in source system | Farida Sheikh | Medium | 100000 | Open | 2026-09-08 | 2026-09-28
RAID-010 | Risk | Financial | Vendor Onboarding Portal | Spend is outpacing progress, budget overrun likely if unaddressed | Priya Nair | High | 700000 | Open | 2026-09-12 | 2026-09-26
RAID-011 | Risk | Regulatory/Compliance | Compliance Reporting Upgrade | Regulator may change submission format before release | Amit Deshmukh | High | 350000 | Open | 2026-08-20 | 2026-10-12
RAID-012 | Assumption | Regulatory/Compliance | Compliance Reporting Upgrade | Current regulatory templates remain valid till Q4 review | Priya Nair | Low | 0 | Open | 2026-08-20 | 2026-10-12
RAID-013 | Issue | Resourcing | Compliance Reporting Upgrade | Lead Business Analyst allocation dropping week over week | Priya Nair | Medium | 0 | Open | 2026-09-10 | 2026-09-24
RAID-014 | Dependency | Technical | Employee Self-Service Portal | Depends on IT Security sign-off for production access | Vikram Joshi | Medium | 0 | Mitigated | 2026-08-15 | 2026-09-15
RAID-015 | Assumption | Process | Employee Self-Service Portal | No further scope changes accepted post Wk3 | Farida Sheikh | Low | 0 | Open | 2026-09-08 | 2026-09-30
RAID-016 | Risk | Vendor/Third-Party | Digital KYC Enhancement | Third-party ID verification API still in beta | Neha Kapoor | High | 500000 | Open | 2026-08-30 | 2026-09-28
RAID-017 | Issue | Technical | Digital KYC Enhancement | Integration test failures on edge-case document types | Ritu Malhotra | Medium | 120000 | Open | 2026-09-05 | 2026-09-20
RAID-018 | Dependency | Regulatory/Compliance | Digital KYC Enhancement | Depends on updated KYC policy approval from Compliance | Neha Kapoor | Medium | 0 | Open | 2026-09-01 | 2026-09-22
RAID-019 | Assumption | Data | Digital KYC Enhancement | Existing customer ID images meet new resolution standard | Ritu Malhotra | Low | 0 | Open | 2026-09-01 | 2026-09-30
RAID-020 | Risk | Process | Branch Analytics Rollout | Early rollout branches reported unclear dashboards, adoption risk | Suresh Iyer | High | 250000 | Mitigated | 2026-08-22 | 2026-09-08
RAID-021 | Issue | Resourcing | Branch Analytics Rollout | Rollout paused for a week due to reviewer unavailability | Arjun Menon | Medium | 60000 | Closed | 2026-08-25 | 2026-09-01
RAID-022 | Dependency | Technical | Branch Analytics Rollout | Depends on regional network upgrade completing by Wk4 | Suresh Iyer | Medium | 0 | Open | 2026-09-01 | 2026-09-15
RAID-023 | Risk | Financial | Branch Analytics Rollout | Recovery push in Wk4 may require unbudgeted contractor support | Suresh Iyer | Medium | 180000 | Open | 2026-09-13 | 2026-09-30