Steering Committee Meeting Minutes

Technizer PMO  |  Week of 08 September 2026

## Attendees

- Priya Nair (PMO Lead) - Chair

- Karan Bhatia (Senior PM, Loan Origination Revamp & Collections Dashboard)

- Vikram Joshi (Senior PM, Employee Self-Service Portal & Collections Dashboard)

- Neha Kapoor (Senior PM, Digital KYC Enhancement)

- Suresh Iyer (Senior PM, Branch Analytics Rollout)

- Rohan Mehta (PMO Analyst)

- Sneha Kulkarni (Project Coordinator, Vendor Onboarding Portal)

## Discussion

Vendor Onboarding Portal (Red)

- Data migration approach remains unapproved by Legal; this is now the single biggest blocker to the 22-Sep milestone.

- Spend has reached INR 28.0L against a planned budget of INR 50.0L, well ahead of the 25% completion level.

- Decision: Priya Nair to escalate directly to the Head - Procurement this week and request a joint call with Legal.

Loan Origination Revamp (Amber)

- Vendor API delivery has slipped twice; Rohan Mehta to get a written revised date before the next review.

- Aditi Rao flagged she is stretched across this project and Collections Dashboard; PMO to monitor her allocation.

Digital KYC Enhancement (Amber)

- Third-party ID verification API is still in beta. Neha Kapoor to track certification status weekly and report any change immediately, not just at the next steering committee.

Compliance Reporting Upgrade (Amber)

- Regulator may change the submission format ahead of the Q4 release. Amit Deshmukh preparing for the 12-Oct regulator preview session.

Branch Analytics Rollout (Amber)

- Recovering well after the early Red status; adoption issue from Week 1 has been resolved.

- Suresh Iyer noted the team may need short-term contractor support to hold the recovery pace through Week 4, to be costed and brought back if needed.

## Action Items

| Action | Owner | Due |
| --- | --- | --- |
| Escalate Vendor Onboarding Portal Legal sign-off to sponsor | Priya Nair | 12-Sep-2026 |
| Obtain written revised API delivery date from vendor | Rohan Mehta | 15-Sep-2026 |
| Weekly check-in on Digital KYC third-party API certification | Neha Kapoor | Ongoing |
| Cost out contractor support option for Branch Analytics recovery | Suresh Iyer | 13-Sep-2026 |

Next steering committee: 15 September 2026