## Slide 1
Portfolio Status Update
Week of 08 September 2026 | Technizer PMO Steering Committee Review

## Slide 2
Portfolio RAG Summary
Project | Project Manager | % Complete | RAG
Loan Origination Revamp | Karan Bhatia | 50% | Amber
Collections Dashboard | Karan Bhatia | 75% | Green
Vendor Onboarding Portal | Priya Nair | 25% | Red
Compliance Reporting Upgrade | Priya Nair | 60% | Amber
Employee Self-Service Portal | Vikram Joshi | 85% | Green
Digital KYC Enhancement | Neha Kapoor | 40% | Amber
Branch Analytics Rollout | Suresh Iyer | 30% | Amber

## Slide 3
Budget Snapshot
Project | Planned Budget (INR) | Actual Spend to Date | Variance vs. Progress
Loan Origination Revamp | 85.0L | 43.0L | +1.2%
Collections Dashboard | 32.0L | 24.5L | +2.1%
Vendor Onboarding Portal | 50.0L | 28.0L | +124%
Compliance Reporting Upgrade | 40.0L | 24.5L | +2.1%
Employee Self-Service Portal | 28.0L | 22.0L | -7.6%
Digital KYC Enhancement | 60.0L | 30.0L | +25.0%
Branch Analytics Rollout | 35.0L | 17.0L | +61.9%
Variance vs. Progress compares actual spend to date against what the plan implies for this stage of completion. L = INR lakh.

## Slide 4
Key Risks & Watch Items
Project | Risk / Issue | Impact | Owner
Vendor Onboarding Portal | Data migration approach not yet approved by Legal | High | Priya Nair
Loan Origination Revamp | Vendor may miss API delivery date again | High | Rohan Mehta
Digital KYC Enhancement | Third-party ID verification API still in beta | High | Neha Kapoor
Compliance Reporting Upgrade | Regulator may change submission format before release | High | Amit Deshmukh
Vendor Onboarding Portal | Key vendor SME on extended leave | Medium | Sneha Kulkarni

## Slide 5
Next Steps
Vendor Onboarding Portal: escalate Legal sign-off timeline to sponsor
Loan Origination Revamp: confirm revised vendor delivery date before next review
Digital KYC Enhancement: track third-party API certification status weekly
Compliance Reporting Upgrade: prepare for regulator preview session on 12-Oct